## Sheet1
(Tasks gotten from Assignments in canvas, what we're being graded on. Might not be all tasks. Does not include peer evaluations/status)
(I'm putting the start date of each as the end date of the previous for now, but we'll want to tweak that.)
Aaron
Benjamin
Stephen
All
Task | Start | Duration | End |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
 | time axis 2019-03-27 to 2019-05-29
Project Proposal | 2019-03-27 | 7 | 2019-04-03
Use Cases | 2019-04-03 |  | 2019-04-10
Prototype/Wireframes | 2019-04-10 |  | 2019-04-17
Research AI with Python and How to implement
0
->Research Python AI
Setting up Wiki resource | 2019-04-03 |  | 2019-05-29
Preliminary Gantt Chart | 2019-04-03 |  | 2019-05-29
Database Design/Entity Relationship | 2019-04-17 |  | 2019-04-24
Midterm | 2019-04-17 |  | 2019-04-24
Activity Diagrams | 2019-04-24 |  | 2019-05-01
Final Gantt Chart | 2019-05-01 |  | 2019-05-22
Final Presentation | 2019-05-22 |  | 2019-05-29
Final Wiki | 2019-05-22 |  | 2019-05-29
Calendar
Inventory
Modal for inventory
option to separate seasonal inventory
(Tasks after this will be for next qtr, don't need yet)
Task 12
Task 13
Task 14
Task 15