## Sheet1
Project MiniGreen
Week # 9
Team Members
Benjamin Waters - Aaron Hebert - Stephen Lawson
Project Summary
Gannt Chart has been updated for this quarter and completed for the next quarter.
Tasks organized and assigned to different individuals.
Team Members |  | Hours Worked
Ben Waters |  | 4
Stephen Lawson |  | 3
Aaron Hebert |  | 4
Completed Tasks from Past Week |  | Task Owner
Gannt Chart completed and updated for next quarter |  | All
Machine Learning Review |  | Ben
Planned Time | Actual Time | Remaining Hours in Budget
6 hours | 4 hours | 12
Planned Tasks for Next Week |  | Task Owner
Finish Final Presentation |  | All
Updated wiki |  | All
Project Risks |  | Severity (High, Med, Low)
Possibly being late with the powerpoint and wiki updates |  | Low
Overdue Tasks
None
Issues
None
Follow Up Actions |  | Responsible Person
None