## Sheet1
Project MiniGreen
Week 1
Team Members
Benjamin Waters - Aaron Hebert - Stephen Lawson
Project Summary
Algorithms for creating dummy data is done
MongoDB successfully talking to Django (can read/write data)
Database is at first version
Team Members |  | Hours Worked
Aaron |  | 4
Completed Tasks from Past Week |  | Task Owner
Planned Time | Actual Time | Remaining Hours in Budget
Planned Tasks for Next Week |  | Task Owner
Prototype Frontend that displays dummy data |  | Aaron
Project Risks |  | Severity (High, Med, Low)
Risk of other classes interfering with schedule |  | Medium
Overdue Tasks
Prototype Frontend
Issues
Follow Up Actions |  | Responsible Person
Get a single working url to display custom HTML |  | Aaron