## Sheet1
Project MiniGreen
Week #8
Team Members
Benjamin Waters - Aaron Hebert - Stephen Lawson
Project Summary
The group created sequence diagrams for several processes within the program.
Efforts were made on improving the Gantt chart, and researching machine learning.
Team Members |  | Hours Worked
Ben Waters |  | 6
Aaron Hebert |  | 3
Stephen Lawson |  | 2
Completed Tasks from Past Week |  | Task Owner
Sequence Diagram- 2 Hours |  | Stephen Lawson
Machine Learning - 4 hours, Sequence Diagrams -2 hours |  | Ben Waterse
Gantt Chart - 1 Hour, Sequence Diagrams - 2 hours |  | Aaron Hebert
Planned Time | Actual Time | Remaining Hours in Budget
14 Hours | 11 hours | 12 Hours
Planned Tasks for Next Week |  | Task Owner
Finish Gantt Chart |  | Aaron Hebert, Stephen Lawson
Project Risks |  | Severity (High, Med, Low)
Overdue Tasks
None
Issues
None
Follow Up Actions |  | Responsible Person
N/A