## Sheet1
Project MiniGreen
Week # 7
Team Members
Benjamin Waters - Aaron Hebert - Stephen Lawson
Project Summary
This week, we worked primarily on class diagrams, with their association and internal workings.
Further efforts were made toward researching machine learning.
Team Members |  | Hours Worked
Aaron Hebert |  | 3 Hours
Stephen Lawson |  | 3 hours
Ben Waters |  | 8 hours
Completed Tasks from Past Week |  | Task Owner
Class Diagrams - 4 hours, Machine learning review - 4 hours |  | Ben Waters
Class Diagrams - 2 Hours, Django Documentation - 1 Hour |  | Aaron Hebert
Class Diagrams - 2 Hours, Review sequence diagrams - 1 hours |  | Stephen Lawson
Planned Time | Actual Time | Remaining Hours in Budget
6 hours | 8 Hours | 18 hours
Planned Tasks for Next Week |  | Task Owner
Sequence Diagrams |  | All
Gantt Chart |  | Aaron Hebert
Machine learning review |  | Ben Waters
Project Risks |  | Severity (High, Med, Low)
Burnout - Mitigation, take breaks |  | High
Overdue Tasks
Gantt Chart
Issues
No current issues
Follow Up Actions |  | Responsible Person
Dedicate time to work on Gantt Chart |  | Aaron Hebert