## Sheet1
Project MiniGreen
Week 1
Team Members
Benjamin Waters - Aaron Hebert - Stephen Lawson
Project Summary
Team Members |  | Hours Worked
Aaron |  | 4
Benjamin |  | 7
Stephen |  | 5
Completed Tasks from Past Week |  | Task Owner
Algorithms for creating dummy data is done |  | Ben
MongoDB successfully talking to Django (can read/write data) |  | Aaron
Database is at first version |  | Stephen
Planned Time | Actual Time | Remaining Hours in Budget
Planned Tasks for Next Week |  | Task Owner
Prototype Frontend that displays dummy data |  | Aaron
Create a format for data in csv file and read the file to the ML algorithms. |  | Ben
Created first version of MongoDB database |  | Stephen
Project Risks |  | Severity (High, Med, Low)
Risk of other classes interfering with schedule |  | Medium
Overdue Tasks
Prototype Frontend
Issues
Some difficulty with formatting in the csv. Just makes progress slow.
Follow Up Actions |  | Responsible Person
Get a single working url to display custom HTML |  | Aaron